## Task List
DGMU HUMAN RESOURCE MANAGEMENT SYSTEM
# | TASK DETAILS | MODULE PARTS | PROGRESS | STATUS | DATE START | DATE ACCOMPLISH | PROCESS | Remarks / Affected Table and Stored Procedures
1 | Fix Picture problem when update action was activate | Employee Data | 100% | COMPLETED | 2018-06-20 | 2018-06-20 | Create boolean variable that will hold if the user change the image or not. Variable Name: IMAGE_CHANGE
2 | Setting up employee salary rate | Employee Payroll Setup | 100% | COMPLETED | 9.27.2018 | 9.28.2018 | •Create two type of Payroll (Branch and Office) •Setup Basic Rate and Actual Rate. •Listed Branch is base on Wage - Branch setup • Adding Manual Salary option. 10.30.2018 •Selecting Branch will display wage amount
3 | Fix Loading of Employee List | Employee Data | 100% | COMPLETED | 9.27.2018 | 9.27.2018 | Remove Image loading in Gridview Row_Databound
4 | Setting up Payroll Salary Wage per Area | Salary Wage Setup | 100% | COMPLETED | 9.28.2018 | 9.28.2018 | • Create and Update Salary wage setup, will be the default of all branches included on this wage Area. • Adding Incentive Employee Multiplier for Senior and Regular Employee (10.24.2018) • Change to call name instead of Salary Wage, "Area Supervisor Wage Setup" • Global update of Salary wage of each employee once wage amount updated (10.29.2018) | This Module will be reference of Branch Payroll in default Basic Rate of each branches link on the Wage Area.
5 | Linking Branch to Wage Area | Branch Wage Setup | 100% | COMPLETED | 9.28.2018 | 9.28.2018 | • Branch - Wage Link is required to Create Branch - Employee Link | In this module the user able to create link the wage and branch.
6 | Linking Branch to Employee | Branch Employee Setup | 100% | COMPLETED | 9.28.2018 | 10.02.2018 | • Branch - Employee Assignment process (OKAY) • Branch - Employee Remove (OKAY) • Cosmetic process (OKAY) | This module only applicable to those employee that will be categorize as branch payroll Group.
7 | Employee Payroll | Data Entry Employee Payroll | 100% | COMPLETED | 10.03.2018 | 10.09.2018 | • Selection of Users: Payroll Group, (Wage List and Branch if Branch Payroll Group selected) (OKAY) • Display List of Employee Base on Selected Payroll Group (Okay) • Display Payroll Input/Salary (OKay) • Edit/Update Payroll ( ) • Computation of Gross (Okay) • Computation of Government Dues (Okay) • Computation of Taxable Income (Okay) • Computation of Total Deduction (Okay) • Computation of Total Net Pay (Okay) • Pagibig Additional Payment for those upgrade their share(OK) • Payroll Period is base what data is active.(OK) • Gov't Dues Remittances data included on Insert and Update of Transaction • Display Salary Loan Balance in Payroll Module |  | STATUS
8 | Payroll Period Setup | Payroll Period Setup | 100% | COMPLETED | 10.09.2018 | 10.10.2018 | • INSERT NEW PAYROLL PERIOD (OKAY) • EDIT/UPDATE (OKAY) • Setting up default Payroll Period |  | ON PROCESS
9 | Payslip Report | PrintPayslip_Batch | 100% | COMPLETED | 10.10.2018 | 10.25.2018 | • Report File (Okay) • Incorporate to WebForm with selection (OKAY) |  | NOT YET STARED
10 | Branch Employee Incentive | Data Entry Branch Incentive | 100% | COMPLETED | 10.11.2018 | 10.26.2018 | • Formula use: Branch Sales - ((Employee Sr Attendance x 47 + Employee Reg Attendance x 55 …) * 6.5) Note Sr and Regular Multiplier depend on the setup on wage • Transfer / Pull Out of Employee from another Branch (Okay) 10.25.2018 • Income pull out data is Net Pay not Gross Pay (Okay) 11.5.2018 (as demonstrated to Bossing) |  | PENDING
11 | Employee Voucher | Data Entry Payroll Voucher | 100% | COMPLETED | 10.12.2018 | 10.20.2018 | • Display only employee that already computed in payroll (OKAY) • Computation of Voucher Total Amount in Stored Procedure (OKAY) • Insert and Update (OKAY) • Printing (On process) |  | COMPLETED
12 | Voucher Report | PrintVoucher_Batch | 100% | COMPLETED | 10.10.2018 | 10.26.2018 | • Report File (Okay) • Incorporate to WebForm with selection (Okay) |  | NOT YET STARED
13 | Incentive Report | PrintIncentive_Batch | 100% | COMPLETED | 10.29.2018 | 10.29.2018 | • Report File (OK) • Incorporate to WebForm with selection (OK)
15 | Gov't Dues Remittance Report | PrintRemittances | 100% | COMPLETED | 11.3.2018 | 11.3.2018 | • Report File (OK) • Incorporate to WebForm with selection (OK)
16 | Employee Loans | dataEntryEmployeeLoan | 100% | COMPLETED | 11.6.2018 | 12.8.2018 | • List of Employee (OKay) • Display Loan Details(okay), • History() and Running Balance(Okay) • Salary Loan Link to Payroll for Deductions (Okay)
17 | Display Birthday List of the Month | Home Page | 100% | COMPLETED | 12.7.2018 | 12.7.2018 | • Display List of Employee with current system Month Birthday | Need to update [HR].[spGET_EMPLOYEE_LIST_LW]
18 | Employee Vacation/Sick Leaves | dataEntryEmployeeLeaves | 75% | ON PROCESS | 12.27.2018 |  |  | Create New Table • [Payroll].[Utility_Leave_Type_RF] • [Payroll].[Employee_Leaves_MF] • [xSystem].[Years_RF] Create Stored Procedure • [Payroll].[spGET_Leaves_List] • [Payroll].[spINSERT_UPDATE_EMPLOYEE_LEAVES] • [Payroll].[spGET_EMPLOYEE_LEAVES_HISTORY] • [Payroll].[spGET_EMPLOYEE_LEAVES_AVAILABLE]
19 | Adjustment on Payslip Government Deduction as Monthly deduction | • Payroll Period Setup • dataEntryEmployeePayroll | 30% | ON PROCESS | 01.09.2019 |  | • Add new field name PPCutOff on Payroll Period Table and Payroll_TF • Adding condition in dataEntryEmployeePayroll reference is PPCutOff if is equal == 1 no government computation | UPDATE TABLES AND STORED PROCEDURE • [Payroll].[spINSERT_PAYROLL_PERIOD_SETUP]
20 | Display Employee Salary Loan Balance | • dataEntryEmployeePayroll | 100% | COMPLETED | 01.09.2019 | 01.09.2019 | • Add order of Salary Loan | • [Payroll].[spGET_EMPLOYEE_SALARY_LOAN_BALANCE]
21 | Adding Branch Wife in Incentive Computation | • dataEntryIncentives • setupWageArea • empPaySetup | 100% | COMPLETED | 01.30.2019 | 01.30.2019 | • Adding Checkbox Branch Wife • Adding Textbox in setupWage for Branch Wife Quota | • [Payroll].[[Payroll].[GET_INCENTIVE_RATE] • [Payroll].[spINSERT_UPDATE_EMPLOYEE_SALARY] • [Payroll].[GET_INCENTIVE_RATE]
22 | Adding New Tab Skills and Training | • EmpData | 100% | COMPLETED | 02.28.2019 | 02.28.2019 | • Adding stored procedures.
23 | Adding New Tab Work Evaluation / Performance | • EmpData | 100% | COMPLETED | 08.14.2019 | 08.15.2019 | Create an employee work evaluation as reference for performance and the value of Employee. | • Adding new table and Stored procedures [TABLES] •[HR]. Utility_Work_Evaluation_Criteria_RF •[HR]. Utility_Work_Evaluation_Ratings_RF •[HR]. Employee_Work_Evaluation_Hdr_MD •[HR]. Employee_Work_Evaluation_Rows_MD [Stored Procedures] •[HR].[spINSERTUPDATE_EMPLOYEE_WORK_EVALUATION] • [HR].[spGET_WORK_EVALUATION_CRITERIA_LIST] • [HR].[spGET_WORK_EVALUATION_RATINGS_LIST] • [HR].[spGET_EMPLOYEE_WORK_EVALUATION_REMARKS] • [HR].[spGET_EMPLOYEE_WORK_EVALUATION_RESULT]
24 | Adding New Tab Offenses Record | • EmpData | 100% | COMPLETED | 08.15.2019 | 08.15.2019 | Create an offenses committed by employee to be recorded for reference in decision of employment | Adding new table and stored procedures [Table] •[HR].[Employee_Offenses_MD] [Stored Procedures] •[HR].[spINSERTUPDATE_EMPLOYEE_OFFENSES] •[HR].[spGET_EMPLOYEE_OFFENSES]
25 | BJ- Multiple Entry New Employee Button | • EmpData | 100% | COMPLETED | 08.31.2019 | 09.01.2019 | Create Modal Loading / update progress | Addding new image for loading.
26 | BJ- Leave Balance equals to zero when creating | • dataEntryEmployeeLeave | 100% | COMPLETED | 08.31.2019 | 09.01.2019 | Update Stored procedure for leave setup | [Stored Procedures] • [Payroll].[spINSERT_UPDATE_EMPLOYEE_LEAVES_SETUP]
27 | Request to allow leave entry even no balance | • dataEntryEmployeeLeave | 100% | COMPLETED | 09.01.2019 | 09.01.2019 | Record and create prompt message for allowing entry even no balance.
28
29
30

## Formula Computation
PAYROLL - PAYSLIP
FORMULA
BASIC PAY | RatePerDay * #work days present
LEAVE | RatePerDay * #leave use
PAY-OFF | RatePerDay * #payoff use
REGULAR OT | ((RatePerDay/8) * 1.25) * #hours // MODIFY Period June 1-15 USE THIS FORMULA ((RatePerDay/8) * 1) * #hours
REGULAR HOLIDAY OT | ((RatePerDay/8) * 2.60) * #hours
SPECIAL HOLIDAY OT | ((RatePerDay/8) * 1.69) * #hours
REGULAR HOLIDAY | (RatePerDay * 1) * #day present
SPECIAL HOLIDAY | (RatePerDay * .30) * #day present
ABSENCE | RatePerDay * #work absent
TARDINESS | ((RatePerDay/8) / 60 ) * #minutes
UNDERTIME | ((RatePerDay/8) / 60 ) * #minutes
SSS | RangeCompensation(BasicPay)
PhilHealth | RangeCompensation(BasicPay) If BasicPay < 10,000 = 275 If BasicPay > 10,000 and BasicPay < 39,999.99 = BasicPay * 2.75 If BasicPay > 40,000 and up = 1100
PagIbig | Fixed 100
Gross Income | Basic Pay + Regular OT + Regular Holiday OT + Special Holiday OT + Regular Holiday + Special Holiday
Deduction Income | Absence + Tardiness + UnderTime + SSS + PhilHealth + PagIbig + Boarding + Cash Advance + Emergency Loan + Salary Loan + SSS LOAN + Pagibig LOAN
Taxable Income | Gross Income - (Absence + Tardiness + Undertime + SSS + PhilHealth + PagIbig)
With Holding Tax | Per cut off basis: If Taxable Income < 10,417 = 0 If Taxable Income > 10,418 and < 16,666 = (Taxable Income - 10,418) * 0.20 If Taxable Income > 16,667 and < 33,332 = (Taxable Income - 16,667) * 0.25 + 1,250
NET PAY | Gross Income - (Deduction Income + With Holding Tax)
13th Month | Basic Pay + Paid Leaves / 12 | reference | https://coins.ph/blog/how-to-compute-for-13th-month-pay-philippines/

## Task CheckList
| TASK NAME | Status | Date Start | Date Done | Remarks
1 | Display Loan Balance in Branch Payslip | CLOSE | 2019-01-28 | 2019-01-28 | None
2 | Incentive computation (Income = Gross - Total Holidays) | CLOSE | 2019-01-28 | 2019-01-28 | Created new stored procedure that will get total holidays computed cited by Ma'am Jean ([Payroll].[spGET_BRANCH_EMPLOYEE_HOLIDAYS_AMOUNT])
3 | Remove Images from Data Entry and Salary Setup List | CLOSE | 2019-01-28 | 2019-01-28 | Decided to remove for data performance
4 | Adding Company Data in Employee Information List | CLOSE | 2019-01-28 | 2019-01-28 | Requested by Ma'am Jemih / Modify Stored Procedure ([HR].[spGET_EMPLOYEE_LIST_LW]) |  | Status
5 | Apply Gross - Holiday Amount in Incentives Print Out | CLOSE | 2019-01-28 | 2019-01-28 | Adding New field in (Branch_Employee_Incentives_TF) and Modify Stored Procedure ([Payroll].[spINSERT_UPDATE_BRANCH_EMPLOYEE_INCENTIVES_TRANSACTION]), Lastly update Views(VR_PAYROLL_BRANCH_INCENTIVES)
6 | Incentive Branch Wife | CLOSE | 2019-01-30 | 2019-01-30 | Adding New Field in empPaySetup and SetupWageArea for Branch Wife Quota |  | ON PROCESS
7 | Gov't Due computation Less the Holiday Amount | ON PROCESS | 2019-01-30 |  |  |  | PENDING
8 | [6 empty] | OPEN
9 | Disable Absent Entry in Payslip Entry Module | CLOSE | 2019-09-03 | 2019-09-07 | Enable = false of Textbox Absent in Paslip Entry. |  | CLOSE
10 | Change Formula table of Regular and Special Non working Holiday | CLOSE | 2019-09-03 | 2019-09-07 | Update Payroll.Payroll_Fixed_Value_RF (RH and SH)
11 | Work Evaluation Section (Insert Date From and Date To) With selection listing of history | CLOSE | 2019-09-08 | 2019-09-10 | Table : [HR].[Employee_Work_Evaluation_Hdr_MD] •Added two fields DateStart and DateEnd
12 | Skills and Training added the company sponsorship selection and date start | CLOSE | 2019-09-09 | 2019-09-12 | Table = [HR].[Employee_SkillsTraining_MD] • Added two fields (StartTrainingDate and IsCompanySponsor) SP = [HR].[spINSERTUPDATE_EMPLOYEE_SKILLSTRAINING] [HR].[spGET_EMPLOYEE_SKILLSTRAINING]
13 | Additional Loan Information Loan Reference # for Government Agency and Monthly Amortization | CLOSE | 2019-09-18 | 2019-09-20 | Table = [Payroll].[Employee_Loan_MF] • Added fields (LoanReferenceNumber, MonthlyAmortization,MA_DateStart and MA_DateEnd) SP = [Payroll].[spINSERT_UPDATE_EMPLOYEE_LOAN]
14 | New Module for Employee Transfer Company | CLOSE | 2019-09-21 |  | New Table : Employee_Company_Transfer_RF • Add new row data in menu name : EMPLOYEE COMPANY TRANSFER • Add new column in Stored procedure [HR].[spGET_EMPLOYEE_LIST_LW] name: CompanyCode SP = [HR].[spINSERTUPDATE_EMPLOYEE_TRANSFER] and [HR].[spGET_EMPLOYEE_COMPANY_HISTORY]
15 | OT Voucher Pay Change Formula, note OT will not included in payslip process | CLOSE | 2019-09-25 | 2019-09-25 | Added new field in Table Payroll_Voucher_Employee_TF • AdditionalWorkDays • OTHours SP = [Payroll].[spINSERT_UPDATE_EMPLOYEE_VOUCHER_TRANSACTION] = [Payroll].[GET_VOUCHER_OVERTIME_PAY]
16 | Display List of Employee doesn't have Gov't ID inputed. | CLOSE | 2019-09-26 | 2019-09-28 | Added new View = HR.VR_EMPLOYEE_NO_GOVT_IDs New Report Name = No_Govt_IDs.rpt New Page = repEmployeeNoGovtID.aspx Added to HR.Menu data = repEmployeeNoGovtID.aspx
17 | Add Princal plus Interest on Gov't LOAN | CLOSE | 2019-09-27 | 2019-09-28 | Add new field in table [Payroll].[Employee_Loan_MF]and [Payroll].[Employee_Loans_Detail_TF] • LoanAmountandInterest (float) Update SP = [Payroll].[spINSERT_UPDATE_EMPLOYEE_LOAN], [Payroll].[spINSERT_UPDATE_EMPLOYEE_LOAN_PAYMENT], [Payroll].[spGET_EMPLOYEE_LOANS]
18 | Display Loan Monthly Amortization automatic on payslip module | CLOSE | 2019-09-27 | 2019-10-01 | Update SP = [Payroll].[spGET_EMPLOYEE_SALARY_LOAN_AMORTIZATION], [Payroll].[spGET_EMPLOYEE_PAGIBIG_AMORTIZATION] [Payroll].[spGET_EMPLOYEE_SSS_AMORTIZATION] Module Affected, Payslip Inhouse
19 | Display Evaluation Percentage in Record List | CLOSE | 2019-09-29 | 2019-10-01 | SP = [HR].[spGET_EMPLOYEE_WORK_EVALUATION_RECORD] Module Affected = empdata.aspx
20 | Attachment of Employee Files | CLOSE | 2019-10-01 | 2019-10-10 | New Table: [HR].[Employee_Attachment_MD] SP = [HR].[spINSERT_EMPLOYEE_ATTACHMENT], [HR].[spGET_EMPLOYEE_ATTACHMENTS], [HR].[spREMOVE_EMPLOYEE_ATTACHMENTS]
21 | Re arrange Employee Status Code for smooth identification of Active and Inactive Employee | CLOSE | 2019-10-11 | 2019-10-12 | Adding Table : [xSys].[Employee_StatusCode_RF] Adding Relationship of [xSys].[Employee_StatusCode_RF] and [HR].[Utility_Employment_Status_RF] = field (Sys_Employee_StatusCode)
22 | Create Employment Type | CLOSE | 2019-10-17 | 2019-10-17 | Adding Table : [HR].[Utility_Employment_Type_RF] SP : [HR].[spGET_EMPLOYMENT_TYPE]
23 | *** Isolate the function of Employment Details Updating | CLOSE | 2019-10-22 | 2019-10-27 | Adding Table : [HR].[Employee_Employment_Details],[HR].[Employee_Govt_ID],[HR].[Employee_Application_Record] Stored Procedure: [HR].[spINSERT_UPDATE_EMPLOYMENT_DETAILS], [HR].[spINSERT_UPDATE_EMPLOYEE_GOVT_ID], [HR].[spINSERT_UPDATE_EMPLOYEE_APPLICATION_RECORD], [HR].[spGET_FULL_EMPLOYEE_LIST]
24 | Employee Children | CLOSE | 2019-10-29 | 2019-10-29 | Adding Table: [HR].[Employee_Family_Children_RF] Stored Procedures: [HR].[spINSERT_UPDATE_EMPLOYEE_CHILDREN], [HR].[spGET_EMPLOYEE_CHILDREN], [HR].[spREMOVE_EMPLOYEE_CHILDREN]
25 | Transfer Incase of Emergency in Family Section Transaction | CLOSE | 2019-10-29 | 2019-10-29 | MODIY TABLE: [HR].[Employee_Family_MD] adding 3 fields, ContactPerson, ContactNumber and ContactRelationship NEW STORED PROCEDURES: [HR].[spINSERT_UPDATE_EMPLOYEE_FAMILY_DATA]
26 | Minimize Basic Information | CLOSE | 2019-10-29 | 2019-10-29 | Create New Stored Procedure: [HR].[spINSERT_UPDATE_EMPLOYEE_BASIC_DATA]
27 | Create Employee Employment History | CLOSE | 2019-10-29 | 2019-10-30 | Create New Table: [HR].[Employee_Previous_Employment_Record_RF] Stored Procedures: [HR].[spINSERT_UPDATE_EMPLOYEE_PREVIOUS_EMPLOYMENT_HISTORY] [HR].[spREMOVE_EMPLOYMENT_HISTORY]
28 | Payslip Module Entry Page, display total Loan seperately. | CLOSE | 2019-10-30 | 2019-10-30 | Update Source Code only and Design of Payslip (Inhouse) and (Store)
29 | Manual Entry of 13th Month Pay | CLOSE | 2019-10-30 | 2019-11-10 | Table : [Payroll].[Manual_13thMonth_TF] Stored Procedures: [Payroll].[spGET_EMPLOYEE_LIST_MANUAL_13TH_MONTH] [Payroll].[spGET_EMPLOYEE_13TH_TOTALWORKSINYEAR] [Payroll].[spINSERT_UPDATE_EMPLOYEE_13TH_MONTH_MANUAL]
30 | Manual 13th Month Report(payslip format) and Billing Format | CLOSE | 12.08.2019 | 12.08.2019 | Create Report Files and Views [Payroll].[VR_13TH_MONTH], [Payroll].[VR_13TH_MONTH_SUMMARY_COMPANY] Pay13Month.rpt and Summary_List_Manual_13thMonth.rpt
31 | Sorting and Fix displaying of Employee Status | CLOSE | 12.09.2019 | 12.09.2019 | Store Procedure: [HR].[spGET_FULL_EMPLOYEE_LIST], [HR].[spGET_EMPLOYEE_LIST_LW], [Payroll].[spGET_EMPLOYEE_LIST_MANUAL_13TH_MONTH] By adding First_Name Field in Query of Order by.
32 | Removing Employee Data | CLOSE | 12.09.2019 | 12.09.2019 | Adding new Field in table [HR].[Employee_MD] IsRemoved(bit), DateRemoved(DateTime) Create New Store Procedure: [HR].[spREMOVE_EMPLOYEE_DATA]
33 | Addin Single Saving in Manual 13th Month Entry | CLOSE | 12.09.2019 | 12.09.2019
34 | ***************** 2020 ****************************************
35 | Payslip Regular Holiday * 200 and Special Holiday * 130 (Not Present Reg Holiday = * 100, Not Present Special Holiday * nothing) | CLOSE | 02.02.2020 | 02.10.2020 | INSERT NEW FIELDS IN TABLE: [Payroll].[Payroll_Employee_TF] (RegularHolidayNP_Qty,RegularHolidayNP,SpecialHolidayNP_Qty,SpecialHolidayNP) [Payroll].[Payroll_Fixed_Value_RF](RHN,SHN) Stored Procedure: [Payroll].[GET_REGULAR_HOLIDAY_NP], [Payroll].[GET_SPECIAL_HOLIDAY_NP], [Payroll].[spINSERT_UPDATE_EMPLOYEE_PAYROLL_TRANSACTION] ****** View [Payroll].[VR_PAYROLL_PAYSLIP] Reports Files Payslips.rpt and Payslips_Branch.rpt
36 | End of Service Function | CLOSE | 02.26.2020 | 03.01.2020 | Additional Data field on [HR].Employee_Employment_Details * EOSDate and EOSRemarks Stored Procedures: [HR].[spINSERT_UPDATE_EMPLOYEE_EOS] | UPLOADED (03.11.2020)
37 | Adding Company Billing, to Isolate billing of Gov't Dues. | CLOSE | 02.28.2020 | 03.01.2020 | Added new Field in Gov't ID table *BillingCompanyCode Store Procedure: -Update [HR].[spINSERT_UPDATE_EMPLOYEE_GOVT_ID] -Update [Payroll].[spINSERT_UPDATE_EMPLOYEE_PAYROLL_TRANSACTION] -Update [Payroll].[REPORT_COMPANY_FOR_BIR_SUMMARY] | UPLOADED (03.11.2020)
38 | Disabling Access of End Of Service Employee in Payroll/Payslip Module | CLOSE | 03.02.2020 | 03.08.2020 | Store Procedure: - Update [Payroll].[spGET_EMPLOYEE_SALARY] | UPLOADED (03.11.2020)
39 | Logs Company To Bill Record of Employee | CLOSE | 03.08.2020 | 03.09.2020 | Stored Procedure -Create [Payroll].[spGET_EMPLOYEE_GOVT_DUES_COMPANY_RECORDS] | UPLOADED (03.11.2020)
40 | Automate Voucher computation once Payslip already process. | CLOSE | 03.09.2020 | 03.10.2020 | Stored Procedure -Update [Payroll].[spINSERT_UPDATE_EMPLOYEE_PAYROLL_TRANSACTION] -Update [Payroll].[GET_VOUCHER_EMPLOYEE_COMPUTATION] Views -Update Payroll.VR_PAYROLL_VOUCHER Report FileName -PayVoucher.rpt | UPLOADED (03.11.2020)
41 | Gov't ID Incomplete remove TIN ID in condition | CLOSE | 03.10.2020 | 03.10.2020 | Views -Update HR.VR_EMPLOYEE_NO_GOVT_IDs Report FileName -No_Govt_IDs.rpt | UPLOADED (03.11.2020)
42 | Fixing Problem in Payslip some employee process the payslip not showing in report | CLOSE | 03.10.2020 | 03.10.2020 | Views -Update Payroll.VR_PAYROLL_PAYSLIP | UPLOADED (03.11.2020)
43 | Pulling method of Gov't Dues Computation base on prev month 2nd cut off + current month 1st cut off | CLOSE | 03.10.2020 | 03.10.2020 | Stored Procedure: -Update [Payroll].[GET_PHILHEALTH_AMOUNT] -Update [Payroll].[GET_SSS_AMOUNT] -Update [Payroll].[GET_WTAX] -Update [Payroll].[spINSERT_UPDATE_EMPLOYEE_PAYROLL_TRANSACTION] | UPLOADED (03.11.2020)
44 | Prevent Displaying Loan deduction once Loan Date not yet meet. | CLOSE | 03.11.2020 | 03.11.2020 | Stored Procedure: - Update [Payroll][.spGET_EMPLOYEE_SALARY_LOAN_BALANCE] - Update [Payroll][.spGET_EMPLOYEE_SALARY_LOAN_AMORTIZATION] - Update [Payroll][.spGET_EMPLOYEE_SSS_LOAN_BALANCE] - Update [Payroll][.spGET_EMPLOYEE_SSS_LOAN_AMORTIZATION] - Update [Payroll][.spGET_EMPLOYEE_PAGIBIG_LOAN_BALANCE] - Update [Payroll][.spGET_EMPLOYEE_PAGIBIG_LOAN_AMORTIZATION] | UPLOADED (03.11.2020)
45 | End of Service Effectivity Date trigger(Disable Employee Payroll Process) | CLOSE | 03.12.2020 |  | Table: - New [HR].[Employee_EOS_RF] Stored Procedure: - Update [HR].[spINSERT_UPDATE_EMPLOYEE_EOS] - Update [HR].[spGET_FULL_EMPLOYEE_LIST] - New [HR].[spGET_RESIGN_APPLICATION] | UPLOADED(06.24.2020)
46 | Create Manual Entry for Gov't Dues | CLOSE | 03.20.2020 | 03.22.2020 | Table: - Create xSystem.[Months_RF] - Create [Payroll].[Payroll_GovtDues_Manual_TF] Stored Procedure: - Create [xSystem].[spGET_MONTHS_LIST] - Create [Payroll].[spGET_EMPLOYEE_GOVTDUES_DAYSPRESENT] - Create [Payroll].[spGET_EMPLOYEE_MANUAL_GOVTDUES_SSS] - Create [Payroll].[spGET_EMPLOYEE_MANUAL_GOVTDUES_PH] - Create [Payroll].[spGET_EMPLOYEE_MANUAL_GOVTDUES_HDMF] -Create [Payroll].[spINSERT_UPDATE_EMPLOYEE_MANUAL_GOVTDUES] View: -Create [Payroll].[VR_EMPLOYEE_GOVTDUE_MANUAL] | UPLOADED (03.24.2020)
47 | Leave Entry connected to Payroll Process | CLOSE | 03.30.2020 |  | Table: - Added field PPID, IsIncludeToPayroll,IsHalfday,IsPayrollProcess,PayableLeave, IsCancel in [Payroll].[Employee_Leaves_TF] Stored Procedure: - Update [Payroll].[spINSERT_UPDATE_EMPLOYEE_LEAVES] - Create [Payroll].[spGET_EMPLOYEE_LEAVE_PAYABLE] - Update [Payroll].[spINSERT_UPDATE_EMPLOYEE_PAYROLL_TRANSACTION] - Create [Payroll].[spREMOVE_UPDATE_EMPLOYEE_LEAVES] | UPLOADED(06.24.2020)
48 | Modification of Employee Listing Display with Icon | CLOSE | 04.10.2020 | 04.11.2020 | Stored Procedure: - UPDATE [Payroll].[spGET_EMPLOYEE_SALARY] | UPLOADED(06.24.2020)
49 | Uploade Image of Employee | CLOSE | 05.01.2020 | 05.01.2020 | Table: Added field (EmployeePicture) [HR].[Employee_MD] Stored Procedures: -Create [HR].[spINSERT_UPDATE_EMPLOYEE_PICTURE] -Create [HR].[spGET_EMPLOYEE_PICTURE] Resources: Added Folder name (EmployeePictures) in existing folder (Uploads) | UPLOADED(06.24.2020)
50 | *** JUNE 2020 ***
51 | Computed 13th Month per month conjunction with Payslip Process Action | ON PROCESS | 6.26.2020 | 06.26.2020 | Table: -CREATE [Payroll].[Employee_13thMonth_TF] Stored Procedures: -CREATE [Payroll].[spINSERT_UPDATE_EMPLOYEE_13TH_MONTH] * (Incorporate to [Payroll].[spINSERT_UPDATE_EMPLOYEE_PAYROLL_TRANSACTION]) -UPDATE [Payroll].[spINSERT_UPDATE_EMPLOYEE_PAYROLL_TRANSACTION]
52 | Summary Report 13th Month Breakdown Per Company | ON PROCESS | 6.26.2020
53 | Adjust text-font of Payslip and Performance Bonus Inhouse&Store | CLOSE | 6.26.2020 | 6.26.2020 | Update Report File of Payslip and Voucher.rpt FONT USE in DotMatrix Printer: Calibri Light | ULOADED 6.26.2020
54 | Adjust Inhouse Performance Bonus Company Heading | CLOSE | 6.26.2020 | 6.26.2020 | Views: -UPDATE [Payroll].[VR_PAYROLL_VOUCHER] | ULOADED 6.26.2020
55 | Double payslip of 1 employee | CLOSE | 6.26.2020 | 6.26.2020 | Views: -UPDATE [Payroll].[VR_PAYROLL_PAYSLIP] (Need to add filter LoanCode = 'SA' and LoanCode Is Null) UPDATE Need to remove Table of Loan MF and filter only SA on query command. | ULOADED 6.26.2020
56 | Edit Entry of Employee Loan | CLOSE | 6.28.2020 | 06.30.2020 | Table - Adding field name DU in Payroll.Employee_Loan_MF Store Procedure -UPDATE [Payroll].[spINSERT_UPDATE_EMPLOYEE_LOAN] -CREATE [Payroll].[spEDIT_UPDATE_EMPLOYEE_LOAN] | UPLOADED 6.30.2020
57
58
59

## Notes
Notes
1 | Leave With Pay will be entry by HR Department and automatically pullout by Payroll process | base on Ma'am Grace | 03.11.2020
2 | Performance Bonus inclusion of (Days work + Leave with Pay) | base on Ma'am Grace | 03.11.2020 | ok
3 | Implement User Account Setup |  | 03.11.2020
4 | Ma'am Jemih need to update HR Side. |  | 03.11.2020
5 | Once date resign trigger give 15 Days grace period to compute payroll | Ma'am Jemih | 03.10.2020
6 | Once resign but covered by 2nd cut off don’t compute Gov't Due | Ma'am Jemih | 03.10.2020
7 | Create New Company Account for dummy and edit Company to Bill. | Ma'am Jemih | 03.10.2020
8 | End of Service Effectivity Date Notification. | Ma'am Jemih | 03.04.2020
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26