## Task List
DGMU HUMAN RESOURCE MANAGEMENT SYSTEM
# | TASK DETAILS | MODULE PARTS | PROGRESS | STATUS | DATE START | DATE ACCOMPLISH | PROCESS | Remarks / Affected Table and Stored Procedures
1 | Fix Picture problem when update action was activate | Employee Data | 100% | COMPLETED | 2018-06-20 | 2018-06-20 | Create boolean variable that will hold if the user change the image or not. Variable Name: IMAGE_CHANGE
2 | Setting up employee salary rate | Employee Payroll Setup | 100% | COMPLETED | 9.27.2018 | 9.28.2018 | •Create two type of Payroll (Branch and Office) •Setup Basic Rate and Actual Rate. •Listed Branch is base on Wage - Branch setup • Adding Manual Salary option. 10.30.2018 •Selecting Branch will display wage amount
3 | Fix Loading of Employee List | Employee Data | 100% | COMPLETED | 9.27.2018 | 9.27.2018 | Remove Image loading in Gridview Row_Databound
4 | Setting up Payroll Salary Wage per Area | Salary Wage Setup | 100% | COMPLETED | 9.28.2018 | 9.28.2018 | • Create and Update Salary wage setup, will be the default of all branches included on this wage Area. • Adding Incentive Employee Multiplier for Senior and Regular Employee (10.24.2018) • Change to call name instead of Salary Wage, "Area Supervisor Wage Setup" • Global update of Salary wage of each employee once wage amount updated (10.29.2018) | This Module will be reference of Branch Payroll in default Basic Rate of each branches link on the Wage Area.
5 | Linking Branch to Wage Area | Branch Wage Setup | 100% | COMPLETED | 9.28.2018 | 9.28.2018 | • Branch - Wage Link is required to Create Branch - Employee Link | In this module the user able to create link the wage and branch.
6 | Linking Branch to Employee | Branch Employee Setup | 100% | COMPLETED | 9.28.2018 | 10.02.2018 | • Branch - Employee Assignment process (OKAY) • Branch - Employee Remove (OKAY) • Cosmetic process (OKAY) | This module only applicable to those employee that will be categorize as branch payroll Group.
7 | Employee Payroll | Data Entry Employee Payroll | 100% | COMPLETED | 10.03.2018 | 10.09.2018 | • Selection of Users: Payroll Group, (Wage List and Branch if Branch Payroll Group selected) (OKAY) • Display List of Employee Base on Selected Payroll Group (Okay) • Display Payroll Input/Salary (OKay) • Edit/Update Payroll ( ) • Computation of Gross (Okay) • Computation of Government Dues (Okay) • Computation of Taxable Income (Okay) • Computation of Total Deduction (Okay) • Computation of Total Net Pay (Okay) • Pagibig Additional Payment for those upgrade their share(OK) • Payroll Period is base what data is active.(OK) • Gov't Dues Remittances data included on Insert and Update of Transaction • Display Salary Loan Balance in Payroll Module |  | STATUS
8 | Payroll Period Setup | Payroll Period Setup | 100% | COMPLETED | 10.09.2018 | 10.10.2018 | • INSERT NEW PAYROLL PERIOD (OKAY) • EDIT/UPDATE (OKAY) • Setting up default Payroll Period |  | ON PROCESS
9 | Payslip Report | PrintPayslip_Batch | 100% | COMPLETED | 10.10.2018 | 10.25.2018 | • Report File (Okay) • Incorporate to WebForm with selection (OKAY) |  | NOT YET STARED
10 | Branch Employee Incentive | Data Entry Branch Incentive | 100% | COMPLETED | 10.11.2018 | 10.26.2018 | • Formula use: Branch Sales - ((Employee Sr Attendance x 47 + Employee Reg Attendance x 55 …) * 6.5) Note Sr and Regular Multiplier depend on the setup on wage • Transfer / Pull Out of Employee from another Branch (Okay) 10.25.2018 • Income pull out data is Net Pay not Gross Pay (Okay) 11.5.2018 (as demonstrated to Bossing) |  | PENDING
11 | Employee Voucher | Data Entry Payroll Voucher | 100% | COMPLETED | 10.12.2018 | 10.20.2018 | • Display only employee that already computed in payroll (OKAY) • Computation of Voucher Total Amount in Stored Procedure (OKAY) • Insert and Update (OKAY) • Printing (On process) |  | COMPLETED
12 | Voucher Report | PrintVoucher_Batch | 100% | COMPLETED | 10.10.2018 | 10.26.2018 | • Report File (Okay) • Incorporate to WebForm with selection (Okay) |  | NOT YET STARED
13 | Incentive Report | PrintIncentive_Batch | 100% | COMPLETED | 10.29.2018 | 10.29.2018 | • Report File (OK) • Incorporate to WebForm with selection (OK)
15 | Gov't Dues Remittance Report | PrintRemittances | 100% | COMPLETED | 11.3.2018 | 11.3.2018 | • Report File (OK) • Incorporate to WebForm with selection (OK)
16 | Employee Loans | dataEntryEmployeeLoan | 100% | COMPLETED | 11.6.2018 | 12.8.2018 | • List of Employee (OKay) • Display Loan Details(okay), • History() and Running Balance(Okay) • Salary Loan Link to Payroll for Deductions (Okay)
17 | Display Birthday List of the Month | Home Page | 100% | COMPLETED | 12.7.2018 | 12.7.2018 | • Display List of Employee with current system Month Birthday | Need to update [HR].[spGET_EMPLOYEE_LIST_LW]
18 | Employee Vacation/Sick Leaves | dataEntryEmployeeLeaves | 75% | ON PROCESS | 12.27.2018 |  |  | Create New Table • [Payroll].[Utility_Leave_Type_RF] • [Payroll].[Employee_Leaves_MF] • [xSystem].[Years_RF] Create Stored Procedure • [Payroll].[spGET_Leaves_List] • [Payroll].[spINSERT_UPDATE_EMPLOYEE_LEAVES] • [Payroll].[spGET_EMPLOYEE_LEAVES_HISTORY] • [Payroll].[spGET_EMPLOYEE_LEAVES_AVAILABLE]
19 | Adjustment on Payslip Government Deduction as Monthly deduction | • Payroll Period Setup • dataEntryEmployeePayroll | 30% | ON PROCESS | 01.09.2019 |  | • Add new field name PPCutOff on Payroll Period Table and Payroll_TF • Adding condition in dataEntryEmployeePayroll reference is PPCutOff if is equal == 1 no government computation | UPDATE TABLES AND STORED PROCEDURE • [Payroll].[spINSERT_PAYROLL_PERIOD_SETUP]
20 | Display Employee Salary Loan Balance | • dataEntryEmployeePayroll | 100% | COMPLETED | 01.09.2019 | 01.09.2019 | • Add order of Salary Loan | • [Payroll].[spGET_EMPLOYEE_SALARY_LOAN_BALANCE]
21 | Adding Branch Wife in Incentive Computation | • dataEntryIncentives • setupWageArea • empPaySetup | 100% | COMPLETED | 01.30.2019 | 01.30.2019 | • Adding Checkbox Branch Wife • Adding Textbox in setupWage for Branch Wife Quota | • [Payroll].[[Payroll].[GET_INCENTIVE_RATE] • [Payroll].[spINSERT_UPDATE_EMPLOYEE_SALARY] • [Payroll].[GET_INCENTIVE_RATE]
22 | Adding New Tab Skills and Training | • EmpData | 100% | COMPLETED | 02.28.2019 | 02.28.2019 | • Adding stored procedures.
23 | Adding New Tab Work Evaluation / Performance | • EmpData | 100% | COMPLETED | 08.14.2019 | 08.15.2019 | Create an employee work evaluation as reference for performance and the value of Employee. | • Adding new table and Stored procedures [TABLES] •[HR]. Utility_Work_Evaluation_Criteria_RF •[HR]. Utility_Work_Evaluation_Ratings_RF •[HR]. Employee_Work_Evaluation_Hdr_MD •[HR]. Employee_Work_Evaluation_Rows_MD [Stored Procedures] •[HR].[spINSERTUPDATE_EMPLOYEE_WORK_EVALUATION] • [HR].[spGET_WORK_EVALUATION_CRITERIA_LIST] • [HR].[spGET_WORK_EVALUATION_RATINGS_LIST] • [HR].[spGET_EMPLOYEE_WORK_EVALUATION_REMARKS] • [HR].[spGET_EMPLOYEE_WORK_EVALUATION_RESULT]
24 | Adding New Tab Offenses Record | • EmpData | 100% | COMPLETED | 08.15.2019 | 08.15.2019 | Create an offenses committed by employee to be recorded for reference in decision of employment | Adding new table and stored procedures [Table] •[HR].[Employee_Offenses_MD] [Stored Procedures] •[HR].[spINSERTUPDATE_EMPLOYEE_OFFENSES] •[HR].[spGET_EMPLOYEE_OFFENSES]
25 | BJ- Multiple Entry New Employee Button | • EmpData | 100% | COMPLETED | 08.31.2019 | 09.01.2019 | Create Modal Loading / update progress | Addding new image for loading.
26 | BJ- Leave Balance equals to zero when creating | • dataEntryEmployeeLeave | 100% | COMPLETED | 08.31.2019 | 09.01.2019 | Update Stored procedure for leave setup | [Stored Procedures] • [Payroll].[spINSERT_UPDATE_EMPLOYEE_LEAVES_SETUP]
27 | Request to allow leave entry even no balance | • dataEntryEmployeeLeave | 100% | COMPLETED | 09.01.2019 | 09.01.2019 | Record and create prompt message for allowing entry even no balance.
28
29
30

## Task CheckList
| TASK NAME | Status | Date Start | Date Done | Remarks
1 | Display Loan Balance in Branch Payslip | CLOSE | 2019-01-28 | 2019-01-28 | None
2 | Incentive computation (Income = Gross - Total Holidays) | CLOSE | 2019-01-28 | 2019-01-28 | Created new stored procedure that will get total holidays computed cited by Ma'am Jean ([Payroll].[spGET_BRANCH_EMPLOYEE_HOLIDAYS_AMOUNT])
3 | Remove Images from Data Entry and Salary Setup List | CLOSE | 2019-01-28 | 2019-01-28 | Decided to remove for data performance
4 | Adding Company Data in Employee Information List | CLOSE | 2019-01-28 | 2019-01-28 | Requested by Ma'am Jemih / Modify Stored Procedure ([HR].[spGET_EMPLOYEE_LIST_LW]) | Status
5 | Apply Gross - Holiday Amount in Incentives Print Out | CLOSE | 2019-01-28 | 2019-01-28 | Adding New field in (Branch_Employee_Incentives_TF) and Modify Stored Procedure ([Payroll].[spINSERT_UPDATE_BRANCH_EMPLOYEE_INCENTIVES_TRANSACTION]), Lastly update Views(VR_PAYROLL_BRANCH_INCENTIVES)
6 | Incentive Branch Wife | CLOSE | 2019-01-30 | 2019-01-30 | Adding New Field in empPaySetup and SetupWageArea for Branch Wife Quota | ON PROCESS
7 | Gov't Due computation Less the Holiday Amount | ON PROCESS | 2019-01-30 |  |  | PENDING
8 | [5 empty] | OPEN
9 | [5 empty] | CLOSE
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38